## Read me
Item | Explanation
Purpose | Model a project cost and fee floor from your own scope and assumptions. This is not a market-rate recommendation.
Data | All prefilled numbers and organizations are synthetic. They are not client results, market rates or vendor benchmarks.
How to use | Copy the workbook. Replace assumptions with approved inputs. Preserve sources, units and responsible owners. Excel recalculates formulas when opened.
Review | The worksheet is an editorial method. It has not been reviewed or endorsed by a named finance, legal or engineering practitioner.
Limits | Checking arithmetic does not verify a source, establish causation, certify compliance or predict a career outcome.
Version | October 7, 2026

## Estimate
Activity | Hours | Internal cost per hour (USD) | Cost (USD)
Discovery | 16 | 100
Delivery | 80 | 100
Review | 24 | 100
Handover | 8 | 100
Labor total
Direct project costs |  |  | 2000
Cost contingency fraction |  |  | 0.2
Modeled cost including contingency
Target project contribution margin |  |  | 0.35
Fee floor under these assumptions
Contribution at modeled floor
Exclusions |  |  | Taxes, company overhead not allocated above, sales time, financing and unpriced change requests

## Scope and change
Decision | Your entry | Why it matters
Client problem and evidence |  | A deliverable is useful only if it serves a real decision
Included outputs |  | Name output, review and handover
Acceptance conditions |  | Agree what done means before a fixed fee
Dependency owner |  | Access, clean inputs and client review can alter effort
Change trigger |  | New entity, workflow, data source or approval step may require a new estimate
Capacity use |  | Time released by AI is not automatically cash savings or additional sales

## Rollout observation
Workflow | Affected role | Concern / desired result | Trial task | Observed result | Owner / next action
Synthetic example: first report draft | Preparer | Avoid retyping while preserving traceability | One permitted source packet | Not yet collected | Assign owner
Same workflow | Reviewer | Avoid unsupported explanations | Check each sampled assertion | Not yet collected | Assign reviewer
Same workflow | Approver | Know what changed and who owns it | Review version and exceptions | Not yet collected | Assign approver